## Workplan
The Global Campus Working Group Consists of the entire WMO EC Panel of Experts for ETR and Selected Volunteers work directly with WMO Staff Coordinators on initiatives indicated below
EC-70
| 2016 | 2017 | 2018 | 2019
CALENDAR/CATALOGUE, 2 Prototypes decided: Moodle initially, with WIS investigation | 1. MOODLE: CIMH will host the calendar with work starting 1 May 2016. 2. EC Panel Demo – all EC panel to have loaded courses onto the Calendar for this demo. 3. Operational Prototype by end of 2016 and will need a team to load and test. 4. EC Panel to write a user guide. 5. The Focus on loading aviation training 6. WIS: Request through EC for CBS to investigate calendaring 7. Progress and refine Metadata and QA needs for offerings to the calendar, building on details from EC panel papers 9 and 12, ensure that MD details are consistent with the needs for cataloguing (i.e. catalogue is an aim, so can Moodle be adapted to archive this and then transported to WIS....) 8. Investigate methods for the Moodle and WIS catalogue to host training resources and link to additional training resources beyond those available through the calendar (i.e., resource books, papers or tutorials available online. | 1. CMIH will maintain the Moodle calendar and members will add content to the calendar. 2. EC panel to work with CBS to define WIS calendar process and contribution governance. 3. Define catalogue in WIS, building on Moodle work. 4. Recommend to EC the required Metadata and QA needs for offerings to the calendar. | 1. EC, catalogue –
SUPPORT Members/ETRO/Panel | ETRO - Pat/Mustafa and Selected WG Members
CLIMATE SERVICES | 1. Gather more details and information of offerings, courses, modules, other resources etc.…... 2. Finalize Competencies 3. Liaise/consult/input into any potential Development of BIP-CS or similar 4. Upload resource metadata to first version of the catalogue. | 1. Mature Climate Services Actions
SUPPORT Members/ETRO/Panel | ETRO - Pat
COMMUNICATIONS | 1. 6 – monthly newsletter 2. Benefit Stories of Calendar and All WMO Global Campus 3. Define Communications 4. Identify Challenges 5. Define feedback mechanism 6. Gather benefit stories for aviation training 7. Guiding principles
SUPPORT Members/ETRO/Panel | ETRO - Jeff
SYMET | 1. Input to the Symet Business case, e.g. Calendar Target Audience/User Training , Customer Support/Mechanisms of GC. 2. Further actions will be defined pending decision from EC-68 regarding the proposal of a WMO ETR Symposium to be held in 2017.
SUPPORT Members/ETRO/Panel | ETRO - Jeff/Pat and Selected WG Members
QUALITY | 1. Informal Editorial Board 2. See Calendar 3. Share final draft of proposed working mechanism of the review board. | 1. Formal Editorial Board 2. See Calendar | 1. Formal Editorial Board 2. See Calendar | 1. Formal Editorial Board 2. See Calendar
SUPPORT Members/ETRO/Panel | ETRO - Pat and Selected WG Members
ROADMAP | 1. Draft the Roadmap | 1. Finalise the Roadmap
SUPPORT Members/ETRO/Panel | ETRO - Jeff/Pat and Selected WG Members
FUNDING NEEDED | 1. Seek Funding for WIS catalogue | Seek Funding | Seek Funding | Seek Funding
SUPPORT Members/ETRO/Panel | ETRO - Jeff/Pat and Selected WG Members

## Working Group Members
Home Country | Region | Gender | Title | Family Name | Given Name
Spain | 6 | M | Dr. | Aguillar | Enric
Kenya | 1 | F | Ms | Aura | Stella
Argentina | 3 | F | Dr. | Campetella(*) | Claudia
China | 2 | M | Dr. | DONG | Zhanghang
British Caribbean Territories | 4 | M | Dr. | Farrell | David
USA | 4 | M | Dr. | Jeffries | Richard
South Africa | 1 | F | Dr. | Jordaan(*) | Winifred
China | 2 | M | Dr. | LIU | Zhiyu
Russian Federation | 6 | F | Dr. | Mamaeva | Maria
Canada | 4 | F | Ms | Milton | Jennifer
France | 6 | M | Mr | Reboux | Didier
New Zealand | 5 | M | Mr | Webster(*) | Chris