VLab actions list

Actions resulting from VLMG-4

| Action No.* | Action | Actionee | Deadline | Status July 2010 |
| --- | --- | --- | --- | --- |
| 4.3 | EUMETSAT to finalise the editing of the HPTE DVDs in English, Spanish and Portuguese languages and provide 200 (tbc) copies to WMO SPO for onward distribution to VL network participants and WMO Members. Status: still trying to work on improvements to ease the display of VisitView behind fire walls. | G. Bridge | 31 Dec 2008 | Will be finalised end July with all available lectures and uploaded to EUMETSAT and VLab websites. |
| 4.5 | CMA to investigate possibilities to translate the four HPTE lectures into the Chinese language. Status 14/10/09: translations ongoing | H. Fan | 31 Dec 2009 | 12/7/2010: Could be done when convenient |
| 4.10 | CMA to report back, at the next online meeting of VLMG, on its investigation of possible periodic training sessions for neighbouring countries Status 14/10/09: RFG activity might not be carried out by CMA. ZHU Xiaoxiang is now the deputy director general of National Met Centre of CMA and might facilitate it. Hong Fan will push it in due time. | H. Fan | March 2009 | 12/7/2010 CMA isn´t doing it but Nanjing is doing a lot of activity to train the neighbouring countries |
| 4.11 | VRL task team members plus JMA, to propose a format for the centralised WMO VLab website/portal and for a common look and feel website for the CoE/RFGs. VLMG proposed to use the EUMETSAT and JMA VLab websites as a starting point. Status: 7 VLab websites | Task team: T. Mostek, G. Bridge, V. Castro, A. Kwarteng, J. Kagenyi, L. Peres and Z. Wang | End of 2009 | See agenda item: Concurrent Working Group Meetings, 13/7 |
| 4.12 | EUMETSAT to coordinate the setting up of a joint satellite operator training course on polar orbiting EO satellites, to be held towards the end of 2009. Proposal to be sent to VLMG members Status 12/10/09: have to be discussed and postponed to 2010 | H. Verschuur, | Dec 2008 / Jan 2009 | See agenda item: Developing the training plan, 14/7 12/7/2010: If of interest this topic can be discussed during VLMG-5 |

Actions resulting from CGMS-37

| Action No. | Action | Actionee | Deadline | Status June 2010 |
| --- | --- | --- | --- | --- |
| 37.12 | VLab Co-chairs to discuss with VLab sponsoring agencies the funding of the Technical Support Officer (TSO) position from 2010 onwards. Status: INPE paid the TSO´s salary from November 2009 to January 2010 NOAA / CIRA committed funding of the TSO for 2010 | Volker, Luiz | CGMS-38 | Ongoing |
| 37.14 | WMO to continue dialogue with ISRO regarding the establishment of a CoE and the co-sponsoring of the CoE in Oman. Status January 10: CoE in Oman sent a letter to IMD on 26 Dec 2009 |  | CGMS-38 | Ongoing |
| 37.15 | VLab Co-chairs and WMO to seek an agreement between CGMS, COMET and WMO with a view of using ESRC as a resource library for the VLab. Status: VLMG members have been invited to register and test the functionalities of the ESRC until June 2010 (ref. Action VLMG5.03) | Volker, Luiz, Jerome | CGMS-38 | To be finalised at VLMG-5 See agenda item: Using ESRC as the VLab Resource Library, 14/7 |
| 37.16 | The Co-chairs, in consultation with the WMO Space Programme and other relevant WMO Departments, to prepare a roadmap towards widening the scope of VLab activities to serve the needs of emerging scientific communities in the developing countries. This roadmap will be reviewed by VLMG and presented to CGMS-38 for approval. Status: Communication process started with the WMO Research Department (L. Barrie) | Volker, Luiz, Jerome | CGMS-38 | To be discussed at VLMG-5 See agenda item: Developing a roadmap for widening the scope of the VLab, 14/7 |

Actions resulting from web meetings (VLMG03 - VLMG07)

| Action No. | Action | Actionee | Deadline | Status June 2010 |
| --- | --- | --- | --- | --- |
| VLMG03.05 | VLab members are encouraged to review the current version of WMO document 258, section 7.9, in particular, and to provide any comments and/or proposals for updates to the task team. | All | 31.12.2009 | Final stage See agenda item: Doc 258, chapter 7.9, 13/7 |
| VLMG05.02 | Register and test the functionalities of the ESRC | All | 30.06.2010 | Hands-on session 16/7 in Beijing |
| VLMG05.03 | Co-chairs to prepare exchange of letters between WMO and COMET regarding the use of the ESRC | Volker, Kathy-Ann | 30.09.2010 | See agenda item: Using ESRC as the VLab Resource Library, 14/7 Has been agreed and approved at ET-SUP-5 and |
| VLMG05.06 (ref.: VLMG-4, Action 4.11) | Work on VLab harmonised websites and use the forum on VLab Moodle site for the further exchange of proposals on common elements to be included on all VLab websites and possible changes in the central CGMS VLab website | Task team | 31.01.2010 | See agenda item: Concurrent Working Group Meetings, 13/7 |
| VLMG06.08 | Create reporting template for satellite operating agencies (see action 4.13) | Luciane / Maryam | 31.05.2010 | Draft created, will be discussed at VLMG-5 See agenda item: Concurrent Working Group Meetings, 13/7 |

*Note: The action numbers will be renamed unless there are any rejections to the suggestion made by Volker during the VLMG-5 meeting